## To Buy
To Buy List | Who
Batterns | Mark
Ply Board for clubhouse | Mark
Plasterboard | Mark
Screws | Mark
Plumbing Pipe | Mark
Plumbing Connections | Mark
Exposed Showers | Mark
Toilet Connectors | Mark
Firrings for showers | Mark
Spotlights | Mark
Soil Pipes | Mark
Soil Pipe Fittings | Mark
UPVC trim | Mark
Interior Trims | Mark
Exterior Corner Trims | Mark
Water Tanks | Ben
Fuse Spurs | Mark
Water tank cables | Mark
water shower pumps | Mark
conduit | Mark
Flooring for clubhouse | Ben
Kitchen Units | Mark
End Panels | Mark
Work tops | Mark
Ref Shower | Mark
Fuse Board | Mark
Cesspool | Ben
Armoured cable (cabin to cabin) | Mark
Exterior Paint | Ben
Interior paint | Ben
Ref room door | Ben
Toilet Door locks | Ben
Architrave | Mark
Skirting | Mark
MDF for player booths | Mark
Signage | Ben
Hooks | Ben
Silicone & chaulk
Taps
Facias & soffits
Guttering
UPVC trims for away
Line Marking Paint
Security Cameras & Alarm

## To Do
General | Who | Home Changing Room | Who | Clubhouse | Who
Signage & Fence Posts | Ben | Re-wire fuse board |  | send broken window measurement
Buy a Cesspool | Ben | fit spotlighs |  | new door frame exterior
Digger for spoil pips & cesspool | Ben | wire in heaters |  | fit exterior door
water pipes | Picton | cut out spots for shower room |  | re-board outside
electrics | Mark | re-wire shower room |  | guttering
grass cut | Ben | fill holes from toilet |  | fix roofs
pitch mark out | Ben | 2nd coat paint doorways and toilet |  | level floor
mower blade hire | Ben | paint shower room |  | bolt floors together
mower nipple grease gun | Ben | paint shower ceiling |  | noggins around windows and door
kitchen | Mark | fit shower walls |  | plasterboard
Get a back door | Ben | firrings on shower tray |  | box in all joins
Lloyd collect stuff | Wilf & Mark | shower floor |  | lay hardboard floor
MDF pick up and cut | Mark | tile shower |  | re-wire
Buy flooring | Ben | fit showers |  | water pipes
Buy water tanks (Mark to advise which ones) | Ben | plumbing for showers |  | plumbing for toilets
Chase UKPN | Ben | plumbing for sinks |  | cut out soil holes for toilets
Bank Accounts | Ben & Mark | waste for all |  | fit soil pipes
Chase Football Foundation Grant | Ben | pumps for water |  | plumbing for sinks
Clear Car Park | All | take out water softener |  | fit 3 toilets
Strim edges of pitch | All | build player booths |  | plasterboard toilet walls
Skip Pick Up | Mark | paint player booths |  | fit doors
Order a skip | Mark | trim back wall |  | fit kitchen
Load new skip | All | facia & soffits |  | fit bar
Goals | Ben | guttering |  | re-wire spotlights
Speak to Council | Ben | repair all roofs |  | fit lights
Corner Flags | Ben | fit new outside lights |  | heating
Chase up security fencing | Ben | re-wire fridge point |  | re-wire kitchen
Security Camera & Alarm Install | Simmo | flooring over joins |  | fit new fuse board
Epos Payment System | Ben | trim all walk ways |  | Paint
Insurance | Ben | Refs Room |  | Lay flooring
Brewery Install | Ben | New door |  | Lay kitchen flooring
Air con in cold room |  | Water supply |  | lay toilet flooring
Away Changing Room |  | Plumbing |  | All skirting
High Bond | All | Re-wire |  | All architraves
Paint Outside | All | Build 2 walls |  | Plumbing for kitchen
Make new facia wood |  | Make new interior door |  | Waste for kitchen
Do new facia and soffits |  | fit door |  | lock for kitchen door
Guttering |  | fit door linings |  | noggins for all old windows
2nd Door Lock |  | lay new floor |  | high bond exterior
Plumbing |  | plumb shower and sink |  | paint exterior
Fit toilet |  | fit shower |  | trim all exterior
Fit toilet cubicle |  | fit toilet cubicle |  | silicone all windows
Fit sink |  | fit sink |  | silicone all trims
Waste pipes |  | benches |  | build steps / ramp
Fit taps and waste |  | Paint |  | guttering and water butts
Plumbing for sink and toilet |  | Plaster board walls |  | water supply stuff
Re-wire water tanks |  | re-wire cold room |  | corner trims
re-wire through to shower room |  | box in beer pipes |  | window trims
Silicone all showers |  | lights
Trim all showers |  | guttering
Take off existing showers |  | Fix roof
Wire in heaters
fit spotlights
sort join in flooring
chaulk and silicone all trims
hooks for benches